## Sheet1
site_type | draft_site_id | site_id | land_ownership | MH_notes | BM_notes | landowner_contact | landowner_url | proposed_latitude | proposed_longitude | latitude | longitude | parcel_id | logger_serial | completed_permits | Line_locates | field_install_date | last_download | location_notes | permitting_notes
well | 1A | well_site_2 | BLM | road access looks good | confirmed good access |  |  | 60.5971 | -151.2127 | 60.6024 | -151.2041 | 04101020 | 675669 |  | Submitted 6/28 | 2022-07-04 |  | near powerlines. barometric pressure logger #82786 | sent in application for "casual use" permit 6/21/22. No issues anticipated, final confirmation available afternoon of 7/5/22
well | 2A |  | Alaska Mental Health Trust | road access looks good | confirmed good road access. will contact AMHT | 907-269-7960 | https://alaskamentalhealthtrust.org/connect/contact-info/ | 60.5702 | -151.1641 |  |  | 04103005 |  | Y | Submitted 6/22 |  |  |  | Landowner originally proposed a no-cost agreement; then supervisor came back to require a $300 annual fee. Paid fee.
well | 3A | well_site_4 | USFWS | [6 empty] | 60.6416 | -151.0809 |  | 472877 |  |  | 2022-07-04 |  | "Deep" well
well | 3A | well_site_3 | USFWS | road access looks good | confirmed good access |  |  | 60.6395 | -151.0809 | 60.6416 | -151.0809 | 02514016 | 447555 | Y | Submitted 6/22 | 2022-07-04 |  | "Shallow" well | emailed Stephen Miller 5/20/2022. Permit finalized 6/3/2022
well | 4A | well_site_1 | City of Kenai | road access looks good | confirmed good road access |  |  | 60.5646 | -151.1176 | 60.5644 | -151.1192 | 04103060 |  | Y | Submitted 6/28 | 2022-07-04 |  | near city of kenai water pump station/tanks | emailed DNR public info office at dnr.pic@alaska.gov. Emailed Scott Curtin w/ CoK 6/20/2022.
well | 5A |  | BLM & Alaska Mental Health Trust | road access looks good | confirmed good road access. will contact AMHT |  |  | 60.6126 | -151.1849 |  |  | 01722002 |  | Y | No - I think we will just access this for shading if we can get a well in at 1A | 2022-07-04 |  |  | sent in application for "casual use" BLM permit 6/21/22. Option to install on either AMHT or BLM land.
well | 1B |  | Kenai Natives Association | road access might be tricky | road access look OK |  |  | 60.6103 | -151.281 |  |  | 01721001 |  |  |  | 2022-07-04 |  |  | called Kenai Native Assc office on 6/21/22, permission sounds like simple process, should be complete within 1 week. sent application to KRC
well | 2B |  | USFWS | road access looks iffy | road access unclear. access looks difficult. | [8 empty] | - | - | 2022-07-04 |  |  | I THINK WE CAN DROP THIS AS A WELL SITE; MIGHT BE GOOD TO ACCESS FOR SHADING IF THAT IS ALLOWED>
well | 3B |  | Kenai Natives Association | good road access | confirmed good road access |  |  | 60.6207 | -151.1538 |  |  | 01709001 |  |  | Plan to not put well here | 2022-07-04 |  |  | called Kenai Native Assc office on 6/21/22, permission sounds like simple process, should be complete within 1 week. Sent application to KRC
well | 4B | well_site_5 | USFWS | good road access, don’t need if the Hillcorp wells work out | confirmed good road access |  |  | 60.6464 | -151.0171 | 60.6459 | -151.017 | 02511002 | 448886 | Y | Submitted 6/22 | 2022-07-04 |  | upper marathon road | hilcorp higher-ups non responsive to request as of 6/21/2022
temp_logger |  | beaver_creek_usgs_temp_15 | City of Kenai |  | appx 0.5 mi walk upstream from utility corridor intersection |  |  | 60.6204 | -151.0765 | 60.5559 | -151.1287 | 02514016 | 10816960 |  |  | 2022-07-06 | 2022-10-12 | near Juliessen st
temp_logger |  | KWF_beaver_creek_temp_logger | City of Kenai | [6 empty] | 60.5605 | -151.1255 |  | 20012591 |  |  | TBD | 2022-09-14 | long-term KWF site
temp_logger |  | beaver_creek_usgs_temp_14 | City of Kenai |  | flow may not be present; or ephemeral. probably not worth an install, will apply for permit anyways |  |  | 60.6153 | -151.093 | 60.5601 | -151.1265 | 02514016 | 20625008 |  |  | 2022-07-06 | 2022-09-14 | tributary of beaver creek
temp_logger |  | beaver_creek_usgs_temp_10 | Alaska Mental Health Trust |  | flow likely not present. |  |  | 60.6096 | -151.1817 | 60.6167 | -151.0926 |  | 21235340 |  |  | 2023-07-05 | 2022-09-15 | tributary of beaver creek at powerline trail crossing
temp_logger |  | beaver_creek_usgs_temp_7 | USFWS |  | 0.8 miles to nearest road. access feasible but challenging. |  |  | 60.652 | -151.0913 | 60.6202 | -151.079 | 02511002 | 21235341 |  |  | 2023-07-05 | 2022-09-15 | upstream from powerline crossing
temp_logger |  | beaver_creek_usgs_temp_2 | USFWS |  | confirmed good road access |  |  | 60.6406 | -151.0839 | 60.6406 | -151.061 | 02514016 | 21235343 |  |  | 2022-07-06 | 2022-10-04 | adjacent to upper marathon road
temp_logger |  | beaver_creek_usgs_temp_3 | USFWS |  | good trail access |  |  | 60.6152 | -151.0857 | 60.6511 | -151.0908 | 02514016 | 21444843 |  |  | 2022-07-06 | 2022-10-20 | west fork beaver creek, upstream of marathon road
temp_logger |  | beaver_creek_usgs_temp_8 | USFWS |  | appx 1.0 miles to nearests road. access feasible but challenging. |  |  | 60.6502 | -150.9935 | 60.62 | -151.0788 | 02511002 | 21444844 |  |  | 2023-07-05 | 2022-09-15 | upstream from powerline crossing, small tributary coming in from east
temp_logger |  | beaver_creek_usgs_temp_1 | USFWS |  | confirmed good road access |  |  | 60.6452 | -151.0173 | 60.6495 | -151.0048 | 02514016 | 21444869 |  |  | 2022-07-04 | 2022-10-04 | below outlet of beaver lake
temp_logger |  | beaver_creek_usgs_temp_5 | USFWS | [6 empty] | 60.6435 | -151.0885 |  | 21444870 |  |  | 2022-07-06 | 2022-10-20 | west fork beaver creek, upstream of marathon road, small tributary coming in from west
temp_logger |  | beaver_creek_usgs_temp_9 | USFWS |  | confirmed easy walking access |  |  | 60.6407 | -151.0605 | 60.6151 | -151.0861 | 02514016 | 21444872 |  |  | 2023-07-05 | 2022-09-15 | at powerline crossing of beaver creek | not applying for permit here, flow almost certainly not present (note 9/16/2022: was an incorrect assumption)
temp_logger |  | beaver_creek_usgs_temp_6 | USFWS |  | appx 1.25 miles to nearest road, difficult accecss |  |  | 60.6537 | -151.1224 | 60.6404 | -151.0839 | 01313003 | 21444873 |  |  | 2022-07-04 | 2022-10-13 | west fork of upper beaver creek, just downstrem of road
temp_logger |  | 12 | City of Kenai |  | location is ~50' downstream from original shapefile to relocate off private parcel |  |  | 60.5607 | -151.1272 |  |  | 04108013
temp_logger |  | 13 | Alaska Mental Health Trust |  | park near intersection of raven st and spur hwy maybe |  |  | 60.5714 | -151.1463 |  |  | 04103004
temp_logger |  | beaver_creek_usgs_temp_4 | USFWS | [6 empty] | 60.6508 | -151.0912 |  | 21444874 |  |  | 2022-07-06 | 2022-10-20 | west fork beaver creek, upstream of marathon road, small tributary coming in from west
temp_logger |  | beaver_creek_usgs_temp_11 | Snowshoe Gun Club | [6 empty] | 60.5703 | -151.1032 |  | 21488145 |  |  | 2022-08-26 | 2022-10-18 | near snowshoe gun club
temp_logger |  | 16 | City of Kenai |  | appx 0.5 mi walk upstream from utility corridor intersection |  |  | 60.6211 | -151.0797 |  |  | 02514016
temp_logger |  | 17 | City of Kenai |  | location is modified from shapefile, moved to river left bank on to city of kenai parcel. river right parcel is private |  |  | 60.5493 | -151.141 |  |  | 04926126
temp_logger |  |  | City of Kenai |  | call to confirm access permission; had key/permission in 2015-2016, established site |  |  | 60.5712 | -151.0989 |  |  | 02514101 | [6 empty] | Will be able to request permission at next gun club board meeting on July 14th
temp_logger |  |  | City of Kenai |  | confirmed easy walking access |  |  | 60.5603 | -151.1257 |  |  | 04108013 | [6 empty] | new logger arguably not necessary here, KWF already has a logger installed ~50 feet away.
temp_logger |  | 11 | City of Kenai |  | flow may not be present |  |  | 60.5715 | -151.1446 | [9 empty] | flow likely not present
flow_station |  | USGS 15266500 | City of Kenai | [6 empty] | 60.5632 | -151.1212 |  | NA |  |  |  |  | USGS discharge station 15266500 (https://waterdata.usgs.gov/monitoring-location/15266500/#parameterCode=00065&period=P365D)
Note on K1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: see adjacent hidden columns for the original "proposed" lat and long; values show are ACTUAL installed lat and long